## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
|  | 1 | Foundations and Prerequistes for doing the project |  |  |  | 3- Completed
|  | 2 | Project Understanding, Setup, project achitecture and Google sheet Integration |  |  |  | 3- Completed
|  | 3 | Social Media Integration, Content Creation, Optimization |  |  |  | 3- Completed
|  | 4 | Sentiment Analysis, Slack Integration and deployment |  |  |  | 2- In Progress
Note on F1: Imported Author: ====== ID#AAABs4-wLUs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
L
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 |  | Foundations and Prerequistes for doing the project | 23rd sep | 7th Oct | Arya bhawsar | Learn python fundamentals | Done |  | introduction | learned python and jupyter installation | Learned python keywords and Naming Conventions | Learned python datatypes | setup jupyter, solved installation issues | practiced basic python fundamentals,datatypes | Learned python flow controls | learned strings & its methods,slicing | practice on flow control | Revised python string ,covering their methods,slicing | Revised string concept & started function | practiced function in jupyter | practiced string and functions | Learned all function concept
2 |  | Project Understanding, Setup, project achitecture and Google sheet Integration | 8th oct | 22nd oct | Arya Bhawsar | Understood Project setups ,defining architecture and google sheet integration | Done |  | Understand OOPS Concepts | Learned about python packages and modules | Learned about NLP,text wrangling and cleaning | Learned about NLTK,Spacy Library | Revised NLTK and spacy library concept | Understood about the project | Shared my understanding of the project concept | Learned how to install virtual environment step by step | Learned about Hugging Face Transformers | Project understanding interactive session | Revised Hugging Face Transformer | Practice Python Concept | Practice Transformer and Python Concept | Completed Google Sheet Integration
3 |  | Social Media Integration,Content Creation,Optimization | 23rd Oct | 6th Nov | Arya Bhawsar | Learned social media API integration and applied content generation methods through practical implementation | Done |  | Learnt API Integration with twitter | Understand about API Integration | Worked on Facebook API integration | worked on Linkedin API | Interactive and engagement session | Practice about API Integration | Understanding mock data generation | content created using LLM and Groq API | Worked on gsheet connector | Understand LLM Concept | Practice LLM | Interactive and Engagement Session | Understand how to generate different variations of content | Hands on generating different variations of content with template
4 |  | Sentiment Analysis, Slack Integration and deployment | 6th Nov | 20th Nov | Arya Bhawsar | Learned Sentiment Analysis, A/B Testing ,Slack Integration and deployment on streamlit | Done |  | Studied about API | Understand about API | Practice on API concept | Worked on assignment Task | Interactive and engagement session | learned how to optimize content | Learned about Sentiment Analysis | Understand about Slack Integration | Learned about A/B Testing | Revised the A/B Testing | Practice on Content optimization and sentiment Analysis | Understand about Project Workflow | Discussion about Project Presentation | Mock presentation Done
Note on D2: Imported Author: ====== ID#AAABs4-wLUI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: Imported Author: ====== ID#AAABs4-wLVM Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: Imported Author: ====== ID#AAABs4-wLUM Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: Imported Author: ====== ID#AAABs4-wLUY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: Imported Author: ====== ID#AAABs4-wLU8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: Imported Author: ====== ID#AAABs4-wLUw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: Imported Author: ====== ID#AAABs4-wLU0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: Imported Author: ====== ID#AAABs4-wLVA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: Imported Author: ====== ID#AAABs4-wLUU Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: Imported Author: ====== ID#AAABs4-wLUc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: Imported Author: ====== ID#AAABs4-wLUg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: Imported Author: ====== ID#AAABs4-wLUk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: Imported Author: ====== ID#AAABs4-wLVE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: Imported Author: ====== ID#AAABs4-wLUo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: Imported Author: ====== ID#AAABs4-wLVI Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: Imported Author: ====== ID#AAABs4-wLUQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: Imported Author: ====== ID#AAABs4-wLU4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7